## Test Summary Report
Test Summary Report
Project | E-Commerce Web Application |  | Release | v2.4.1
Test Cycle | Sprint 12 — Regression |  | Environment | Staging
QA Engineer | Sarmad |  | Start Date | Nil
Test Lead | Sarmad |  | End Date | Nil
1. Test Execution Summary
Module | Total TCs | Passed | Failed | Blocked | Not Executed | Pass Rate
User Authentication | 12 | 11 | 1 | 0 | 0 | 91.67%
User Registration | 8 | 7 | 1 | 0 | 0 | 87.5%
Product Catalogue | 10 | 10 | 0 | 0 | 0 | 100%
Shopping Cart | 9 | 8 | 1 | 0 | 0 | 88.89%
Checkout & Payment | 15 | 12 | 2 | 1 | 0 | 80%
Order Management | 6 | 6 | 0 | 0 | 0 | 100%
TOTAL | 60 | 54 | 5 | 1 | 0 | 90%
2. Defect Summary
Severity | Total | Open | In Progress | Resolved | Closed
Critical | 2 | 2 | 0 | 0 | 0
High | 2 | 1 | 1 | 0 | 0
Medium | 2 | 1 | 0 | 1 | 0
Low | 0 | 0 | 0 | 0 | 0
3. Observations & Recommendations
✔ Overall pass rate of 90% meets the release threshold of 85%.
⚠ 2 Critical bugs (BUG-001, BUG-004) must be resolved before production release.
⚠ Checkout module has the highest defect density — recommend focused regression on payment flow.
✔ Product Catalogue module is clean with 100% pass rate.
→ Recommend re-test of BUG-002 (login lockout) and BUG-005 (confirmation email) after next build.
4. Sign-off
Role | Name | Date | Comments
QA Engineer | Sarmad | Nil | Approved for release pending Critical bug fixes